## Cover
TEST PLAN
Project Name | ProlTM |  |  | Reviewer | NguyenQuocTrung
Project Code | PTM |  |  | Review date | 2024-10-31
Creator | NguyenQuocTrung |  |  | Approver | NguyenQuocTrung
Version | v1.0 |  |  | Approval Date | 2024-10-31
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2019-12-31 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | CustomerSupport_ScreenDesign_v1.0 - List of requirements to test/not test - Exit criteria for testing - Suspension criteria and resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
CustomerSupport_ScreenDesign_v1.0 |  |  |  | 1
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description: Defines the process for testing the Customer Support functionality.
Responsibilities: Define the roles for the testing team, customer support team, and any stakeholders.
Notes: Any specific notes related to dependencies, resources, or timelines.
| # | Description | Responsibility | Note
| 1 | Define test scope and objectives for Customer Support feature | QA Lead | Ensure alignment with project requirements
| 2 | Assign test cases to appropriate testers | QA Manager | Assign based on experience with similar features
| 3 | Schedule regular meetings with Customer Support team for feedback | QA Lead & Support Manager | Incorporate direct feedback from end-users
Test case design policy
Items: Specifies the design principles and structure for Customer Support test cases.
| # | Items | Note
| 1 | Design test cases to cover common support issues | Focus on real-world scenarios
| 2 | Include both functional and non-functional tests | Cover response time, accuracy, etc.
Quality metric
Description of target: Measure the effectiveness of the Customer Support function.
| # | Items | Target | Note
| 1 | Customer issue resolution rate | ≥ 90% | Based on resolved tickets
| 2 | Average response time | ≤ 2 hours | Measure during peak hours
| 3 | Customer satisfaction score | ≥ 4/5 | Based on customer feedback surveys
Pass/Fail Criteria
Establish criteria for deciding when testing is successful.
| # | Criteria | Priority | Note
| 1 | 80% test case completion for Customer Support | High | Prioritize common user issues first
| 2 | Test successful resolution rate ≥ 90% | High | Ensure system meets resolution targets
| 3 | No major issues reported by Customer Support staff | High | Confirm alignment with support needs
Suspension Criteria and Resumption Requirements
Define criteria for pausing and resuming testing.
| # | Suspension Criteria | Note
| 1 | System crash affecting Customer Support | Halt until system stability is ensured
| 2 | Customer Support team unavailable during scheduled testing | Reschedule testing sessions
| 3 | Major unresolved bugs in support ticketing functionality | Wait for bug resolution before resuming tests
| # | Resumption Requirements | Note
| 1 | All critical bugs resolved |  | Confirm with the development team
| 2 | Customer Support team available to verify test outcomes | Engage support team to test post-fix functionality

## Test Management
Test Management
Test Scope
Define the scope of items to be tested for Customer Support.
# | Items | Description |  | Responsibility | Note
1 | Issue Logging | Verify if issues are logged correctly |  | Test Analyst | Ensure format meets standards
2 | Issue Assignment | Test if issues are assigned to the right personnel |  | Test Analyst | Based on priority and skill
3 | Response Time | Measure average response time for each support case |  | Performance Tester | Evaluate during peak times
4 | Resolution Workflow | Verify resolution steps are followed |  | Functional Tester | Includes escalation steps
5 | Communication Logs | Ensure all customer interactions are logged |  | Functional Tester | For tracking and auditing
6 | Customer Satisfaction | Test the survey process after resolution |  | QA Lead | Feedback collection method
7 | Reporting Accuracy | Test accuracy of metrics and reports generated |  | QA Lead | Confirm with team management
Deliverables
Specify the documents to be delivered at each phase of the test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-12-31 | QA Lead | Project Manager | Includes scope, risks
2 | Test cases | 2024-12-31 | Test Analyst | Testing Team | For all customer support features
3 | Defect logs | 2024-12-31 | Test Analyst | Development Team | Track bugs in real-time
4 | Test report | 2024-12-31 | QA Lead | Stakeholders | Summary of test results
Management method
Describe how the Customer Support testing process will be managed.
# | Object | Method |  |  | Note
1 | Test Case Management | Use of test management tool |  |  | Tool: JIRA or TestRail
2 | Defect Tracking | Bug-tracking software |  |  | Track and assign bugs in real-time
3 | Progress Tracking | Weekly review meetings |  |  | Report status to stakeholders
4 | Communication with Support | Regular feedback sessions |  |  | Align testing with actual support needs
Risks
List the risks associated with the test process and actions to mitigate them
# | Condition |  | Mitigation |  | Contingency
1 | Insufficient testing time due to high priority issues |  | Prioritize critical test cases |  | Schedule additional testing time
2 | Customer Support process changes during testing |  | Update test cases based on new processes |  | Communicate changes to testing team promptly
3 | Limited access to customer data for testing purposes |  | Use anonymized data for testing |  | Work with customer support for data access
4 | Team members lack domain knowledge |  | Conduct training on Customer Support flow |  | Assign experienced testers for support-related cases
Assumption
Assumptions made for the Customer Support testing process.
# | Type | Description
1 | Resource Availability | Support team available to validate test cases
2 | Environment Stability | Stable environment for testing
3 | Data Availability | Access to necessary customer interaction data
Training Plan
Provide training for the test team on Customer Support functionality.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1 | Customer Support Workflow | Overview of support process and ticketing system |  | Customer Support Lead | 2024-08-01 | 2024-09-01
2 | Test Management Tool | How to track test cases and defects |  | QA Lead | 2024-10-01 | 2024-10-01
3 | Data Privacy and Compliance | Handling customer data with confidentiality |  | Legal Team | 2024-12-01 | 2024-12-01
Note on E33: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G33: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B41: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure that the Customer Support functionality is free from critical defects before release, and to verify that it meets the specified requirements and provides a smooth user experience.
Test stages & techniques
List the stages and techniques to be used for testing the Customer Support functionality.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x | x
Black box testing |  |  | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Specify the key features and functions of Customer Support to be tested.
Feature/Function |  | Document which is testing base on |  |  | Note
Customer Issue Logging |  | CustomerSupport_Requirements_V1.0 |  |  | Ensure logging is reliable and clear
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone |  |  |  | Ensure compatibility
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 78.0.3904.97 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
Master Schedule
# | Item | Start Date | End Date
1 | Create test plan
2 | Create test design
3 | Create test case
4 | Execute test and log bugs
5 | Evaluting exit criteria & Test report
6 | Review
| Task | Start day from 9/12/2019 | Duration
| Create test plan | 0 | 0
| Create test design | -1 | 0
| Create test case | -2 | 0
| Execute test and log bugs | -3 | 0
| Evaluting exit criteria & Test report | -4 | 0
| Review | -5 | 1
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | December
|  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Create test plan | Team | bar: December 9
2 | Create test design | bar: December 14
3 | Create test case | bar: December 16
4 | Execute test and logs bug | bar: December 20 to December 27
5 | Evaluting exit criteria & Test report | Team | bar: December 28
6 | Review | Team | bar: December 31

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1
2
3